## Change Information
MASSEBT Change Tracking & Status Log |  |  |  | Updated 10/14/2020 - M Neibert
ID# | Description | Status (General) | Transaction(s) Affected | Discussion/ Resolution/Issues | Primary Driver | Priority | Documentation Status | Scheduled Release Date | NSTAR Status/Schedule | NGRID Status/Schedule | UNITIL Status/Schedule | WMECO Status/Schedule | Suppliers Status/Schedule | Requestor/ Company | Date of Request
Valid Values, if applicable |  | Preliminary Submitted Discussion Consensus Prioritized Estimated Scheduled In Progress Completed On Hold Cancelled Deleted |  |  | 1- Broken 2- Regulatory Req. 3- Proc. Improv. 4- Standardization | 1- Can't wait 2- Most Wanted 3- Reg release | Missing Preliminary Partial Update Pending Complete Reviewed Approved Posted (incl status date) | Apr 15, yyyy Oct 15, yyyy
001 | Change coding of Billed Demand Use MEA01 to identify metered vs. billed, MEA07 for Significance Code | In Progress | 810 USAGE |  | 3. Process Improv. | 3 - Reg release | Partial 01/09/2002 Need redline of format apndx, manual, 810 IG | Company Specific | Unknown | Done 12/01/2001 | Done 12/01/2001 | Sched 1/31/2002 |  | J. Grace Select Energy | 2000-10-27 | Missing
002 | Add Supply Option to Historical Usage Response | In Progress | 867 HIST USAGE | Add codes to indicate customer's current type of energy supply S = Standard Offer D = Fixed Default V = Variable Default C = Competitive Supplier | 3. Process Improv. | 3 - Reg release |  | Company Specific | March 31, 2002 | Done 08/01/01 | Done 09/01/2001 | Sched 02/28/2002 Done (2/13/2002) |  | D. Falkowski MECO | 2001-03-12
003 | Change Type Notification (REF TD) | In Progress |  | Reviewed by Tech Subgroup 04/11/2001 | 3. Process Improv. | 3 - Reg release |  | Company Specific | Unknown | Sched for 04/30/2002 completion | Completion Q1, 2002 | Unknown |  | J. Grace Select Energy | 2000-10-27 | Reviewed
004 | Load Profile Code (REF LO) | In Progress |  | Reviewed by Tech Subgroup 04/11/2001 | 3. Process Improv. | 3 - Reg release |  | Company Specific | Unknown | Done 10/1/2001 | Done 10/01/2001 | Sched 1/31/2002 |  | J. Grace Select Energy | 2001-02-12 | Approved
005 |  | DELETED |  | DOES NOT APPLY TO MA
006 | Asset ID | 2/13/2002 Consensus | 814 ENROLL 814 CONFIRM 814 CHANGE | Updated version discussed at 12/2001 EBT meeting. Draft documentation covering business process, technical implementation, and data transport is needed for review with disco ISO/Load reporting staff before decision to proceed with further evaluation. 1/9/02 - Lisa Burkarth will update documentation for Feb '02 meeting 1/15/2002 - Complete documentation package submitted to listserv by L. Burkarth 2/13/2002 - Reviewed by group, consensus on process. At implementation, Discos will convert existing accounts with bulk update rather than individual change transactions. Discos prep estimates, be prepared to schedule at March meeting, Not a high priority for suppliers. | 3. Process Improv. | 3 - Reg release | Partial - 01/09/2002 Change form submitted (see Discussion notes) 2/13/2002 - Complete |  | Company approval required to begin estimation activity | Evaluation stage Prepare implementation estimates for 3/2002 meeting | Prepare implementation estimates for 3/2002 meeting | Prepare implementation estimates for 3/2002 meeting |  | L. Burkharth WMECO | 2001-02-01 | Received
007 | Muni Aggregator Enrollment/Confirmation |  |  | NSTAR Implementing for Cape Cod aggregation NGRID and WMECO will not support until process is standardized for all aggregations | [5 empty] | Not approved or scheduled |  |  |  | L. Nickerson NSTAR |  | Posted
008 | Add Service Address to MOVE Transaction | Completed | 814 MOVE 814 ENROLL 814 CHANGE | Some discussion - no request or documentation submitted. 12/19/2001 - J. Grace will prepare Change Request & documentation Need supplier consensus 1/9/02 - J. Grace will prepare Change Request & documentation 2/13/2002 - Select update change req & documentation 03/13/02 - Approved by MA EBT | 3. Process Improv. | 3 - Reg release | 01/09/2002 - Missing 2/13/2002 - Update per EBT discussion re: when a BT address is deleted from cust. Record 3/13/02 - Approved. | 2002-10-15 | [5 empty] | J. Grace Select Energy
009 | Confirmation of Change - Response | Completed | 814 CHANGE | - 1/9/2002 - J. Grace to submit as change request w/ documentation 2/13/2002 - Discussion, need to specify expected responses and actions for each type of change. Schedule this implenentation date same as #010 Rejection Reason Codes 3/13/02- some LDC's objected to having ESP's reject their changes. It was also requested that ESP's should track the number of invalid account numbers for discussion. 4/10/02 - consenus was reached to remove ESP mandatory response. 07/10/02 - It was agreed to add the effective Date (DTM*007) to the accepted change repsonse (from LDC) and to a LDC initiated change request. It is understood that this dtae is an expected next read date and may change if the LDC read schedule changes. | 4- Standardization | 3 - Reg release | 01/09/2002 - Missing 2/13/2002 - Update with expected responses for each case 05/03/02 - Completed | [6 empty] | J. Grace Select Energy
010 | Rejection Reason Codes Change codes for consistency with other market areas | Completed | 814 ERROR | In discussion review with gas transactions need supplier consensus before proceeding - Review Dec '01 research notes from NSTAR, WMECO 1/9/02 - agreed to proceed using UIG standard code list - J. Grace will submit with complete documentation - requested to have separate codes for both Supplier Rate and Pricing Code errors - 1/9/2002 Add codes for Asset ID - 2/13/2002 - Edit and complete code list in IG 03/13/02 - Approved | 4- Standardization | 3 - Reg release | Partial - 01/09/2002 Change form submitted 2/13/2002 Update Pending 03/13/02 - Completed | 2003-04-15 | [5 empty] | J. Grace Select Energy
011 | Service Period Start Dates | Completed | Process 814 ENROLL CHANGE | Dist Co send change if billing cycle changes more than 2 cycles ?? New date and Disco Rate |  |  | Missing
012 | D.U.N.S. + 4 modification | Completed | ALL | More discussion needed - see questions from MECO regarding usage 1/9/02 - Continued discussion - Discos will assess cost & complexity when documentation is complete - 2/13/2002 - Request changed (verbally) to require receiving and returning of 13 digits only. PPL Solutions to complete & submit full documentation before 3/2002 meeting for further consideration. 03/13/02 - approved by MA EBT | 4- Standardization | 3 - Reg release | Partial - 01/09/2002 Change form submitted 03/13/02 -Completed | 2002-10-15 |  | Est cost & effort when documentation is complete |  |  |  | T. Carpency PPL Solutions | 12/11/01 Amended 1/8/02 WMECO (J. Beatrice)
013 | New Supplier Rates & Rate changes | DELETED | None | Each LDC establishes their practices. | [9 empty] | M. Alvarado Mass Electric | 2002-02-13
014 | Add Effective date for LDC initiated change requests | Completed | 814 CHANGE | 07/10/02; preliminary discussion revealed consensus on adding effective date for all LDC initiated Change Requests for all data elements. Currently only some change requests come with an effective date (DTM*007). This will be the expected next read date and could change. | 3. Process Improv. | 3 - Reg release | Missing | [6 empty] | Theresa Carpency, PPL Solutions | 2002-07-10
015 | Add ICAP TAG value | Completed | 814-2, 814-4, 814-8 and 867-1 | 7/10/05: If ICAP TAG is blank default to zero value. ICAP value will be 5 positions to the left of the decimal and 3 positions to the right. The 867 transaction will carry the ICAP data in the PSA segment in the Header at the account level. The 814 transaction will carry the ICAP data in the AMT segment in the LIN loop at the account level. | 3- Proc. Improv. | Most Wanted | Approved | 2005-10-15 | 2005-10-15 | 2005-10-15 | 2005-10-15 | 2005-10-15 | When ready | Strategic Energy and Select Energy | 2005-06-01
016 | Add ASI Action Code AC to acknowledge receipt of request for an account that is processed Off-Line | Completed | 814 |  | 3- Proc. Improv. | 3 | Preliminary | 2007-11-01 | n/a | Novermber 2007 | n/a | n/a |  | Patricia McMahon, NGRID | 2006-11-13
017 | Add Drop Reason Codes to LDC Initiated 814 Drop Requests | Completed | 814 Drop |  | 3- Proc. Improv. | 3- Reg Release | Complete |  | 2011-12-01 | 2011-12-01 | 2012-02-01 | 2011 |  | George Behr, ESG | 2010-08-10
018 | Add Net Metering Indicator to 814 Enrollment Responses, 814 Change Requests and 867 Historical Usage | Completed | 814 Enroll Response 814 Change 867 Historical Usage |  | 3- Proc. Improv. | 3- Reg Release | Partial |  | 2011-12-01 |  |  |  |  | Patricia Reno, TransCanada ESG | 7/1/2011 rev. 1/29/15
019 | Add LDC initiated 814 Reinstatement Requests | Completed | 814 Reinstatement |  | 3- Proc. Improv. | 3- Reg Release | Complete |  | 2011-12-01 | 2011-12-01 | 2012-02-01 | Q1 2012 |  | Monica Neibert, ESG | 8/10/2011 (orig 3/29/2010)
020 | Update 820 for POR, addition of RMR segments | Completed | 820 Payment Remittance | POR subcommittee discussion 8/29. Updated CC and 820 IG | 2- Regulatory Req. | 3- Reg Release | Complete | [6 empty] | Joan Jerz, NGRID Monica Neiber, ESG | 10/14/2011 9/5/13
021 | Update 810 for POR, removal of balance segments | Completed | 810 Usage / Invoice | POR subcommittee discussion 8/29. Updated CC | 2- Regulatory Req. | 3- Reg Release | Complete | [6 empty] | Joan Jerz, NGRID Monica Neiber, ESG | 10/14/2011 9/5/13
022 | Update LDC Initiated 814 Change Requests to support LDC Account Number Changes, Address Changes, Meter Changes due to bankruptcy | Discussion | 814 Change Request | Originally discussed on 2/13/13 EBT Call. Escalated on 4/10/13 call. 4/19/13 - Special call to move forward with formal change control. 5/10/13 - Special call to review change control 6/12/13 - Change Control sent to listserve and discussed on EBT call 6/19/13 - Call to set implementation timeline (none determined) | 3- Proc. Improv. | 2- Most Wanted | Complete |  | Can't address until after POR |  | will include in CIS Upgrade |  |  | Alex De La Rosa, GDF Suez Monica Neibert, ESG | 2013-04-19
023 | Administrative update to 820 IG | Completed | 820 |  | 4 - Standardization | 3 -Reg Release | Complete | [6 empty] | ESG | 2013-09-30
024 | Net Metering Indicator addition | In Progress | 814, 867, 810 | 8/12/15 - Approved. NGRID to implement ASAP. Unitil with system conversion. Eversource when possible | 3- Proc. Improv. | 2 - Most Wanted | Pending IG update |  | TBD | ASAP | 6 months | N/A - ECL has net meter indicator |  | ESG | 2015-07-27
025 | Net Metering Indicator addition | Preliminary | 810 |  | 3 - Proc Improv | 3 | [7 empty] | Daryush Donyavi - Eversource | 2017-01-19
026 | Administrative update to 814 IGs | Submitted | 814E, H, C, D, R, M | Update verbiage for N1*8R to clarify Name Key format | 4 - Standardization | 1 - Can't Wait | Preliminary | 2017-10-31 | N/A | ASAP | N/A | N/A |  | Monica Neibert, ESG | 2017-07-31
027 | Add new REF02 Code CAB to REF*7G on 814E responses | Submitted | 814E |  | 3- Proc. Improv. | 1 - Can't Wait | Complete | TBD |  | n/a | n/a |  |  | Denese Magalid - Eversource | 2018-04-25
028 | Add new REF02 Code C14 to REF*7G on 814C responses | Submitted | 814C |  | 3- Proc. Improv. | 1 - Can't Wait | Complete | TBD |  | n/a | n/a |  |  | Denese Magalid - Eversource | 2018-04-25
029 | Restore Gray Box info for REF*QY segment on 810 | Submitted | 810 | Add back gray box notes for REF*QY | 1 - Broken | 3-Reg Release | Update Pending | TBD | n/a | n/a | n/a | n/a |  | Mary Do - Big Data Energy | 2018-05-24
030 | Correct MEA04 code and Decimal | Submitted | 810, 867 |  | 1 - Broken | 1 - Can't Wait | [7 empty] | Kim Wall - Hansen | 2019-02-13
031 | Add REF*BF Bill Cycle segment to 867H | Submitted | 867H |  | 3 - Proc Improv | 3 - Reg release | Preliminary | 2019-05-01 | n/a | n/a | n/a | 2019-05-01 |  | Denese Magalid - Eversource | 2019-03-14
032 | Add REF03 DIV for REF*7G for 814 | Approved 2/10/21 | 814E, C, D | Submitted 10/14/2020. Eversource implementing in CT so also implementing in MA, NH. Approved 2/10/21 | 3 | 3 | Approved | Q4 2020, Q1 2021 | n/a | n/a | n/a | Q4 2020, Q1 2021 |  | Denese Magalid - Eversource | 2020-10-14

## Update History
Update History - MASSEBT Change Tracking & Status Log
Update By: | Date | Notes
Ken H - MECO | 2002-01-09 | Initial Draft
Ken H - MECO | 2002-01-15 | Updated with notes from 1/9/2002 EBT Meeting Circulated to listserv
Ken H - MECO | 2002-02-04 | Updated per 12/01 ans 01/02 Meeting Notes
J Grace - Select Energy | 2002-07-08 | Updated per 03/13/02 Meeting Minutes
M Neibert - ESG | 2013-07-30 | Historical updates
M Neibert - ESG | 2018-06-05 | Added new change controls 027 - 029
M Neibert - ESG | 2019-04-04 | Updated with CC 030 & 031