## Guide
| National Grid |  | Telco | National Grid | Applicant | National Grid or Applicant | National Grid | Applicant
Stages | Application Acceptance or Rejection | Survey Completion | Telco Reconciliation | Design Reviewed & Make Ready Estimate Sent to Applicant | Make Ready Acceptance/Payment | Make Ready Completion | License issued | Attachment Verification Form | **Post Construction Survey
Preliminary Status | 5 business days
Status 20 |  | 45 days from date of survey payment (+ any time for Telco Reconciliation)
Status 20 |  |  | Survey results/make ready design sent to Telco. Telco to provide feedback or concur ASAP
Status 40 |  |  |  | 14 days from survey completion
Status 40 |  |  |  |  | 14 days from M/R Invoice Date
Status 50 | [5 empty] | Internal Construction: 45 days from M/R payment External Construction: 90 days from M/R Package Received Date
Status 70 | [6 empty] | 14 Days after M/R signed-off by NGRID Supervisor
Status 80 or 90 (Closed) | [7 empty] | Due 90 days after license is granted
Status 80 or 90 (Closed) | [8 empty] | 30 days from completion of install
Total | 5 Days | 50 Days | *14 - 90 Days | 64 - 140 Days | 78 - 154 Days | Internal: 123 - 199 Days External: 168 - 244 Days | Internal: 137 - 213 Days External: 182 - 258 Days | Internal: 227 - 303 Days External: 272 - 348 Days | Internal: 257 - 333 Days External: 302 - 378 Days
*The number of days it takes to reconcile with Telco (joint pole owner) is largely up to the Telco and the applicant. Applicants are required to apply to the joint pole owner when the application is submitted to National Grid. Delays in applicant payment to joint pole owners will delay the reconciliation. Both the design team and the applicant should follow up with telco to ensure the reconciliation is progressed.
For more information on our policies please visit our website: https://www9.nationalgridus.com/niagaramohawk/attachments/policies.asp

## STORMS
WR Status Code | WR Status | WR Status Description
10 | Preliminary Design | Designer Assigned
1X | Cancelled at STATUS 10 | Cancelled at STATUS 10
20 | In Detailed Design | Preliminary Design Completion and Telco Reconciliation
2X | Cancelled at STATUS 20 | Cancelled at STATUS 20
40 | Awaiting Easements/Permits | Applicant Required to Obtain all Permits and Easements (When Required)
40 | In Approval Process | Design Review and Approval Process
4X | Cancelled at STATUS 40 | Cancelled at STATUS 40
50 | Awaiting Scheduling | Pending Applicant MR Completion
5X | Cancelled at STATUS 50 | Cancelled at STATUS 50
60 | Under Construction | Pending Inhouse MR Completion (Only When Ngrid Completes MR)
70 | As-Built Reporting | As-Builts Submission, FCC Review and License Issuance
80 | In Closing Process | Post Construction Survey and Attachment Attestation
90 | Closed | WR Completed and Closed
Job Code Type | Description
DISTTPASAD | Used for Initial Field Survey
DISTTPTYA | Used for Billable Make Ready Work Requests with at least one (1) Capital Work Item – ex. Pole Replacement
DASSETREPL | Used for Non-Billable (PEC) Work Requests with at least one (1) Capital Work Item -- NY ONLY
DISTTPYAMO | Used for Make Ready Work Requests with no Capital Work Item and all Maintenance Work